## Sheet1
Created Date | Name | Milestone | Team | Priority (1=High, 20=Low) | Status | Comments
31/12/2014 | Exploring Automated way to add videos from YouTube Channels (sent 21/9/14) Hi Huy, Last September (21st Sept I believe although I can't find the sent email) we had an idea that we might be able to link up our HWDMediaPlayer to receive notifications when new videos are posted to any YouTube channels that we were tracking, to then be able to either Approve, Edit, or Disgard the video suggestion to be published on PokerWinners.com. We didn't get too deep into how it might work or how much work this would involve as it was only an idea in it's infancy, and it was a low priority we never got around to exploring it, but i'd like to find out whether this would be a possibility and how much work it would involve. Our basic Idea - We would create some development for HWDMediaShare that would be able to follow a number of YouTube Channels such as 'PokerStars', 'ESPN', 'PokerVIP', 'PokerNewsdotcom' and many others and notify us when new content is added (On a daily basis). - These videos would then appear unpublished as pending videos in the HWD backend enabling us to either disgard the videos, or to edit the content (Description/Title) and setup with the relevant information such as which section they should be published too, tags / author etc. - We would simply then be able to go through all of the suggested content from those channels on a day to day basis and publish them to PokerWinners to ensure that we don't miss videos from the channels that we are subscribed too. Hopefully that makes sense? Let me know if it doesn't! It would be good to be able to assign some settings when we follow a channel so that for example we create the channel 'PokerStars', we then choose settings so that all videos that are suggested by this channel will be pre-set with the author to be 'MikeC' , to be posted in the 'TV Shows' video section, and to have the tag 'PokerStars' automatically selected for example. This would mean that whenever a video comes through from that channel the suggested settings above would already be in place so that if we publish the video there and then it will appear in the correct section with the correct author / tags. If you think this sounds viable please can you let us know how big the task would be so that we can see whether this is something we wish to progress with and assign the priority for this. Thanks Michael Copley | 16/04/2015 |  | 5 | In progress | New requests
2015-04-02 | Users IP History Hi Huy, I have a quick question. Do we have details of each IP address that a user has logged on from historically stored within the website database or do we only have this information if a user has posted to the forum? If we have the full data, is it possible that you can send me a full list of the IP's (and username that used that IP) that members have logged on from as we had some funds stolen from a players poker account recently and i'd like to cross check the IP address that was used to enter that account against the history list on PokerWinners to see if we can find out who the person was. I might ask you to add in IP History into the user manager in the future and also a search option to input an IP address to match against users - but we can leave those until a later date so that they don't delay the current developments. Thanks Michael Copley | 18/04/2015 |  | 6 | In progress | New requests
2015-04-10 | Task documents - New 624 modules and changes Hi guys, Please find information about task "New 624 modules required and changes" at the following link: |  |  | 3 | Proposed | New requests
20/5/2015 | [Poker] Some New Hi Tarun, Due to further deterioration of our finances and the lack of a clear picture as to the current status of the ongoing tasks I would like to ask that we halt development after seeing out steps 1-6 listed below to ensure that we can turn around our financial situation over the short-term and that when we resume fuller development we can have a more stable plan in place for better coordination going forward as we have found the last few months challenging in terms of understanding progress, time-frames for completion and having a good communication structure in place. I would like us to follow the following steps to completion: 1) Duplicate a copy of PokerWinners Site to PokerDeals.com I would like to duplicate a copy of the website to PokerDeals.com before we deploy the new homepage header and modules to PokerWinners. We previously spoke to Phong/Huy about this and agreed to copy a full version of the website to a new folder on the same UK Fast server, then we can unlink it so that it performs independently as it's own website under the PokerDeals.com domain name. There is a folder already setup on the server called 'PokerDeals.com' with it's dedicated IP, and RiverOrchid should have the access to our server to be able to duplicate the PokerWinners folder to PokerDeals. We have an existing file showing on PokerWinners (pokerdeals.com/ httpdocs/ index.html ) - please can we leave this holding page displaying on the live site during the copying and database unlinking process. For Further Questions: Please speak to Rick Wild (Skype: wildrick23) 2) Update and Deploy the PokerWinners Header We should update the PokerWinners header changes as outlined in the attached paint file, then deploy this. 3) Provide Full Updates as to Progress of PokerWinners Homepage Modules Please halt the modules development for PokerWinners and provide us with an update for the progress on this task, the number of hours to date, and the hours remaining to deploy 4) Provide Full Updates on Progress of Updating Rankings Calculator on Dev 5) Copy unlinked version of PokerDeals.com to new websites We will then copy the version of PokerDeals to PokerStaking.com, PokerAffiliates.com, iChampion.com.mt, and ChampionCasino.com Please disregard any other instructions until we have received this status update and can provide approval to continue with 3 & 4. Once we have hopefully approved the continuation of 3 & $ we would then like to halt all new development so that we can keep costs to a minimum until we can improve our cash-flow situation. We have other work we would like doing such as optimising for RWD but it's important we reduce our costs to close to nil over the current months until the other areas of our business prove themselves to be sustainable. I understand that this will mean that you can't have someone on standby at all times, however it will only be any rankings fixes that require immediate attention and all other work can be done as and when you have resources available, then as things improve for us we can look to ramp up future development with better structures in place to ensure that it continues as a mutually beneficial partnership over the long-term. I appreciate your understanding. |  |  | 4 | Proposed | New requests
29/5/2015 | Fixes/Changes to Rankings Dropdown, Navigation menu, and Search speed question. Hi Tarun, I notice that Minh and the team have now moved the work on the header from the Dev site to the Live site and made progress on the navigation work and these look good. There are a few changes required however and I have a question about the search function so if you can please forward this email to Minh and the team as I don't believe I have his email and i'm hopeful they might be able to look at these today and give me an answer about the search function before the weekend that would be great. Rankings Drop-down (See Rankings Dropdown attachment) There are three quick fixes required to the ranking drop-down if we can please: 1. Please can we check that when a user selects National Ranking or National Mini-Rankings from the drop-down, that the website will load these pages with the national ranking of whichever country has been selected in the nationality dropdown in the header. Therefore if United Kingdom is selected and the user selects National Ranking from this drop-down then the page will load the United Kingdom National Ranking. When we tested earlier and hit the National Ranking tab there was no data in the page that loaded, as it didn't have nationality selected. 2. Can we change the name of 'Annual LB' and 'Monthly LB' in the drop down to 'Annual Leaderboard' and 'Monthly Leaderboard' respectively 3. When a user is on the page for any of the rankings/leaderboard pages, please can the rankings dropdown at the top of the page be set to the same page we are on (see attachment). For example, when a user is on any Worldwide Rankings page, the dropdown at the top should always read 'Worldwide Rankings' rather than 'View Rankings'. When on any National Rankings pages, the dropdown will show 'National Rankings' etc. Navigation Dropdowns (See Menu Items attachment) The navigation work is currently in progress on the development server but has not gone live yet. Please can we remove the blue drop-down arrows from all of the menu items in the 1st level navigation menu as these are not needed (except for MY PW which was in place before as this not a normal dropdown). Apologies for this as this was probably my mistake in explaining! Please can we also make sure that the items that drop down from the menu are left aligned to the start position for that menu item, instead of right alighned as they are now, and that the text in each menu is also left aligned in the dropdown box. If we can then ensure that all of the menu items are in the correct position instead of 'refer friends' falling off the end on to the row below then we can go live with this. Search Box I notice that the search box that is on the development server has not been moved to our live site yet so I would like to discuss how we can develop the search function (that was made without us realising) into our plans. First of all though any searches we make run very slowly at the moment so I need to find out whether this can be improved to a more acceptable load time as it's too slow at the current time and i guess it will only get slower as our database multiplies in size over the coming months. Do you think we can get the speed to an acceptable time for this? Are there changes we should make to speed it up going forward? If the search speed will not be an issue then I will forward the changes to this search function so that we can develop and go live with this fairly quickly. Please advise. Thanks very much. Progress seems to be smoother since Minh joined the project so thank-you for this. Michael Copley Managing Director Michael Copley Managing Director |  |  | 2 | Proposed | Fix
2015-03-06 | just noticed an annoying rankings glitch [6/3/2015 5:57:53 PM] Minh Bui: on players profile pages, there are 8 specific items that have the same glitch. 4 From the main area at the top - Worldwide rank National rank Annual lb monthly lb And the same 4 in the mini-ranking tab. [6/3/2015 5:58:36 PM] Minh Bui: [6/3/15, 5:57:21 PM] Rick Wild: And the same 4 in the mini-ranking tab. [6/3/15, 5:57:59 PM] Rick Wild: these all display a position, from either the rank upload or user upload. [6/3/15, 5:58:11 PM] Rick Wild: all of them have the same rule.... [6/3/2015 5:59:32 PM] Minh Bui: [6/3/15, 5:58:40 PM] Rick Wild: If a player is not on the upload - display a "?" [6/3/15, 5:59:06 PM] Rick Wild: if a player has ZERO points for the matching points column - display a "?" [6/3/2015 6:01:44 PM] Minh Bui: [6/3/15, 5:59:28 PM] Rick Wild: otherwise, display their position from the column next to the points, on the specific upload. [6/3/15, 5:59:42 PM] Rick Wild: this all works fine [6/3/15, 5:59:45 PM] Rick Wild: and is perfect [6/3/15, 5:59:51 PM] Rick Wild: except for the slight glitch i just noticed [6/3/15, 6:00:14 PM] Rick Wild: which is that it ROUNDS the points figure BEFORE checking if it is zero. [6/3/15, 6:00:46 PM] Rick Wild: so someone with a value of "-0.4" in the points column checked - gets counted as a zero, and a "?" displays instead of their position. [6/3/15, 6:02:49 PM] Rick Wild: his is the current file for rank [6/3/15, 6:02:55 PM] Rick Wild: let me give you 3 examples [6/3/15, 6:03:52 PM] Rick Wild: http://www.pokerwinners.com/profiles/1SweetTooth score in column D = 0 rank displayed as "?" on profile = CORRECT [6/3/15, 6:04:33 PM] Rick Wild: http://www.pokerwinners.com/profiles/7pokkers score in column D = -1.65 rank displayed as 473rd = CORRECT [6/3/15, 6:05:24 PM] Rick Wild: http://www.pokerwinners.com/profiles/3betyourlife score in column D = -0.11 rank displayed as "?" = INCORRECT not zero, should show rank as 461st |  |  | 4 | Proposed | Fix
15/6/2015 | [6/2/15, 9:35:51 PM] Michael Copley: Hi Minh. Please can you do me a favour - the 'PokerWinners: the winning poker community' banner that appears when people are not logged in looks really bad on mobiles. Please can you set this to not appear on mobiles for the moment until we can fix how it displays [6/3/15, 1:50:43 AM] Michael Copley: Also, the slider banner from the homepage also doesn't display well on mobiles so if we can turn this off for now also would be great |  |  | 5 | Proposed | Fix
30/06 | Hi there guys! Hopefully this is a quick fix, we'd like it done asap. The problem concerns the view of this page - http://www.pokerwinners.com/vip-rewards/vip-deals - in firefox and chrome. |  |  |  | Done | Fix
2015-01-07 | [6/30/15, 7:24:18 PM] Rick Wild: hi Minh, we need to make a couple of changes to our main page template [6/30/15, 7:24:26 PM] Rick Wild: to remove a couple of tracking codes and add a new one [6/30/15, 7:25:00 PM] Rick Wild: the file we need to edit is the index.php file in templates/winners_responsive [6/30/15, 7:25:15 PM] Rick Wild: however when editing via joomla i get a "cannot save error" [6/30/15, 7:25:29 PM] Rick Wild: and i am unable to edit in plesk file manager as it is owned by root [6/30/15, 7:25:37 PM] Rick Wild: can you edit it for us please? [6/30/15, 7:25:55 PM] Rick Wild: this text file contains the new version of index.php |  |  |  | Done | New requests
2015-03-07 | both of the leaderboards, monthly and annual; http://www.pokerwinners.com/leaderboards/monthly http://www.pokerwinners.com/leaderboards/annual Show players "previous position" [7/2/2015 5:27:09 PM] Vic ¦ Minh Bui: [7/2/15, 5:24:18 PM] Rick Wild: they are irrelevant when looking at a previous month or previous year [7/2/15, 5:24:35 PM] Rick Wild: so they should only show when we look at the CURRENT month or year. [7/2/2015 5:29:50 PM] Vic ¦ Minh Bui: [7/2/15, 5:26:44 PM] Rick Wild: so if you view the monthly leaderboard for July, in July, you should see previous positions. If you switch to a different month, you shouldn't see them. [7/2/15, 5:28:10 PM] Rick Wild: same with the annual - if you view the CURRENT year, ie 2015, in 2015, then you should see previous positions. If you switch to last years leaderboard, you shouldnt see them. |  |  |  | Done | New requests
2015-07-06 | Fixes to Modules (7th June) 3. Article/Video titles should not be shortened 4. Modules should display article description not intro text 5. Once fixed, these need deploying to live site |  |  | 1 | Done | Fix | Chưa triển khai trên live site
2015-09-06 | New Menu Plan (9th June) None of this work appears to have been done yet: 1. The Hover / Fixed Menu option needs installing (this may have been done but it doesn’t work correctly as once on a fixed menu, the hover option doesn’t work for 1LN) 2. Gaps need removing from the dropdown 3. The change colour background needs implementing when hovering over dropdown 4. Menu needs deploying to the live site |  |  | 1 | Done | Fix | Chưa triển khai trên live site
15/6/2015 | Disable the PokerWinners: the winning community & homepage slider on mobiles |  |  | 1 | Done | New requests
29/5/2015 | Fixes/Changes to the RankingsDropdown The Rankings dropdown work appears to have been done, however on the live site when a user clicks uses the dropdown to select ‘National Ranking’ or ‘National Mini-Ranking’ the page often loads without any country data, 1. Check that when a user selects National Ranking / National Mini-Ranking from header dropdown that the users country will always load within the ranking. |  |  | 1 | Done | Fix | Chưa triển khai trên live site
27/4/2015 | Article List Display Bugs |  |  | 1 | Done | Fix | Chưa triển khai trên live site
2015-07-06 | Fixes to Modules (7th June) 2. Rankings and leaderboard modules don’t work |  |  | 1 | Done | Fix | Chưa triển khai trên live site
21/7/2015 | Homepage Module Tweaks 21st July |  |  | 1 | Done | Fix | Chưa triển khai trên live site
2015-07-06 | Fixes to Modules (7th June) 1. Video module should play on homepage |  |  | 1 | Inprogress | Fix

## Sheet2
[6/30/15, 7:24:18 PM] Rick Wild: hi Minh, we need to make a couple of changes to our main page template [6/30/15, 7:24:26 PM] Rick Wild: to remove a couple of tracking codes and add a new one [6/30/15, 7:25:00 PM] Rick Wild: the file we need to edit is the index.php file in templates/winners_responsive [6/30/15, 7:25:15 PM] Rick Wild: however when editing via joomla i get a "cannot save error" [6/30/15, 7:25:29 PM] Rick Wild: and i am unable to edit in plesk file manager as it is owned by root [6/30/15, 7:25:37 PM] Rick Wild: can you edit it for us please? [6/30/15, 7:25:55 PM] Rick Wild: this text file contains the new version of index.php